## Schedule
Activity ID | Activity Name | WBS | Status | Start | Finish | Duration | % Complete | Predecessors
DES-100 | Detailed Engineering Design | Engineering | Completed | 2024-01-01 | 2024-01-30 | 22 | 100
PROC-200 | Major Equipment Procurement | Procurement | In Progress | 2024-02-01 | 2024-03-15 | 31 | 75 | DES-100FS
CIV-300 | Substructure Construction | Construction | In Progress | 2024-03-01 | 2024-04-15 | 32 | 20 | PROC-200SS+10d
MEP-400 | HVAC & Electrical Installation | Services | Not Started | 2024-04-16 | 2024-05-30 | 33 | 0 | CIV-300FS